## Document Intro
Wendling Beck - Risk plan - BNG
Document purpose
Risk can be understood as the product of the likelihood of an event occuring and the estimated impact of that event. This risk-register is to serve as an example of the potential risks faced by a project/ individual looking to enter into the natural capital markets. It was drafted for the Wendling Beck project for their internal use, however, everyone is likely to face individual risks which need to be carefully considered before changing land-use
Understanding the risk register - column headings
Risk Description | Description of the risk at-hand
Likelihood | Likelihood of the risk manifesting itself
Severity | Impact to the project if the risk were to manifest itself
Mitigating actions | Actions that can be taken to reduce either the likelihood, the severity or both
By Whom | Who will carry out the mitigating actions
By When | When will the mitigating actions be carried out
Actions Complete | Which actions have been completed
Key for Likelihood and Severity |  | Likelihood | Severity
| Low | Unlikely to occur | Low impact (minimal change to project and returns)
| Medium | Could occur | Medium impact
| High | Likely to occur | High impact (possibility of stopping project viability)

## Risk plan
Wendling Beck - Risk plan - BNG
Key |  | Low
Medium
High
Risk Description | Relevant to (BNG/NN): | Likelihood | Severity | Mitigating actions | By Whom | By When | Actions Complete
Financial
Insufficient funding to complete project as planned | Both | Low | High | - Continuous scoping of suitable grants and pro-bono support - Detailed cost planning and generation of business plan and finance model
Project costs exceeding original funding | Both | Medium | Medium | - Strong emphasis on high quality project management and close monitoring of costs
Insufficient demand for environmental credits | Both | Low | High | - Systematic dialogue with local planning authorities to have full transparency on local demand - Diversify buyer base where possible
Price of environmental credits drops undermining the business case (especially where with NN there are multiple different solutions of varying prices) | Both | Low | High | - Systematic dialogue with local planning authorities to have full transparency on pricing developments - Diversify buyer base where possible
Competition (local off-site BNG credits or On-site credits) | BNG | High | Medium | - Understanding DEFRA metric and spatial multiplier, and seeking local demand - Regular attendance of WEBINARs and NEIRF events to understand other existing and potential market participants - Market Research
Other investment
Stacking and bundling risk with alternative investments preventing the future sale of BNG and NN | Both | Medium | Medium
Other?
Policy
Policy not creating enough clarity to foster a condusive market | Both | Low | High | - Closely track policy developments - Engage in active discussions with potential buyers
Risk of policy change removing the market altogether | NN | Medium | High | - Closely track policy developments - Engage in active discussions with potential buyers
Lack of clarity on landowner tax (APR, BPR, CGT, income) | Both | Medium | High | - Commission expert proffesional advice to better understand likely tax liabilities arrising from NbS sales
Unknown changes in biodiversity metric in future iterations | BNG | Medium | Low | - Attend NEIRF and network webinars to stay abreast of planned developments/ changes to the metric
Stacking and bundling to be prohibited lowering financial potential | Both | Medium | Medium | - Assure viable business model even if sole reliance on biodiversity credits is required - Track developments with NE, eftec and other practitioners
Delays to approving and permitting approved solutions to NN offsets | NN | High | Low | - Assure viable business model even if sole reliance on biodiversity credits is required - Track developments with NE, eftec and other practitioners
Lack of monitoring and accountability for infrastructure, reducing demand | Both | Low | Medium | - Where possible engage with Govt. / responsible bodies to ensure high-standards are maintained for infrastructure projects
Operational
Baseline data ages before implementation | BNG | Medium | Low | - Build 2-year implementation start plan. Allowance for re-surveying baseline data if ultimately required
Landowner/ partner disengagement prior to implementation | Both | Low | High | - Ensure good communication and engagement - Build legal agreement to bind landowners and partners (e.g. LLPA)
Essential permissions not granted | Both | Low | Medium | - Early and continous engagement with authorities i.e. Forestry Commission & SSSI Officer